## Project Info
GlimmoraTeam — Feature Delivery Tracker
Standard program register · Phase 1 MVP
Project name | GlimmoraTeam Global Workforce Platform
Document owner | Product / Engineering
Version | 1.0
Last updated | 2026-05-28
Reporting period | Phase 1 (Apr – Aug 2026)
Project manager | [Name]
Engineering manager | [Name]
Status cadence | Weekly — update Assigned To, statuses, and % Complete
Navigation
Sheet | Purpose
Feature Register | Master tracker — edit here
Dashboard | Executive summary (auto-calculated)
Resource Plan | Assignee workload view
Definitions | Column and status definitions

## Feature Register
Feature Register
Single source of truth · Filter by Module, Assigned To, or Overall Status
Feature ID | Module | Feature Name | Description | Priority | Phase | Overall Status | Frontend Status | Backend Status | % Complete | RAG | Assigned To | Accountable (EM) | Planned Start | Planned End | Actual End | Last Updated | Dependency ID | Remarks
FTR-001 | Platform | Application shell & routing | Multi-portal Next.js App Router with role-based layouts | P1 — Critical | Phase 1 — MVP | Completed | Complete | Complete |  |  | Frontend Lead | Engineering Manager | 2026-03-01 | 2026-04-30 |  | 2026-05-28 | — | Production-ready
FTR-002 | Platform | Authentication (email / password) | Login, registration, password reset, session management | P1 — Critical | Phase 1 — MVP | Completed | Complete | Complete |  |  | Backend Lead | Engineering Manager | 2026-03-01 | 2026-04-15 |  | 2026-05-28 | FTR-008 | NextAuth v5 + Prisma
FTR-003 | Platform | OAuth (Google & Microsoft) | SSO sign-in for contributors and enterprise users | P1 — Critical | Phase 1 — MVP | In Progress | Complete | In Progress |  |  | Backend Lead | Engineering Manager | 2026-04-01 | 2026-06-15 |  | 2026-05-28 | FTR-002 | Enterprise IdP routing partial
FTR-004 | Platform | MFA / TOTP | Multi-factor authentication setup and verification | P2 — High | Phase 1 — Hardening | In Progress | Complete | In Progress |  |  | Security Lead | Engineering Manager | 2026-05-01 | 2026-06-30 |  | 2026-05-28 | FTR-002 | E2E coverage pending
FTR-005 | Platform | OTP (email & phone) | One-time password verification flows | P2 — High | Phase 1 — MVP | Completed | Complete | Complete |  |  | Backend Lead | Engineering Manager | 2026-04-01 | 2026-05-01 |  | 2026-05-28 | FTR-011 | Live
FTR-006 | Platform | Role-based route guards | Middleware and hooks enforcing portal access | P1 — Critical | Phase 1 — MVP | In Progress | Complete | In Progress |  |  | Platform Lead | Engineering Manager | 2026-04-15 | 2026-06-01 |  | 2026-05-28 | FTR-002 | Demo bypass flags in dev
FTR-007 | Platform | API authorization (RBAC audit) | requireRole on all API route handlers | P1 — Critical | Phase 1 — Hardening | In Progress | N/A | In Progress |  |  | Backend Lead | Engineering Manager | 2026-05-15 | 2026-06-15 |  | 2026-05-28 | FTR-006 | 2 of 28 routes wired
FTR-008 | Platform | Database schema (Prisma + Postgres) | Core domain models and migrations | P1 — Critical | Phase 1 — MVP | In Progress | N/A | In Progress |  |  | Backend Lead | Engineering Manager | 2026-03-15 | 2026-06-30 |  | 2026-05-28 | — | Schema exists; many domains mock-backed
FTR-009 | Platform | Observability (Sentry / logging) | Error tracking, structured logs, alerting | P1 — Critical | Phase 1 — Hardening | Not Started | N/A | Not Started |  |  | DevOps / SRE | Engineering Manager | 2026-06-01 | 2026-07-15 |  | 2026-05-28 | — | Production blocker
FTR-010 | Platform | Security headers & CSRF | CSP, rate limiting, CSRF middleware | P1 — Critical | Phase 1 — Hardening | Not Started | N/A | Not Started |  |  | Security Lead | Engineering Manager | 2026-06-15 | 2026-07-01 |  | 2026-05-28 | FTR-007
FTR-011 | Platform | Transactional email | Nodemailer + React Email templates | P2 — High | Phase 1 — MVP | In Progress | Complete | In Progress |  |  | Backend Lead | Engineering Manager | 2026-04-01 | 2026-06-01 |  | 2026-05-28 | — | Rate limit + RBAC audit pending
FTR-012 | Platform | Razorpay — order creation | Enterprise milestone payment order intent | P1 — Critical | Phase 1 — MVP | Completed | Complete | Complete |  |  | Backend Lead | Engineering Manager | 2026-04-01 | 2026-05-15 |  | 2026-05-28 | FTR-048 | Gated by acceptance decision
FTR-013 | Platform | Razorpay — webhooks | HMAC signature verification, idempotent events | P1 — Critical | Phase 1 — MVP | Completed | N/A | Complete |  |  | Backend Lead | Engineering Manager | 2026-04-15 | 2026-05-15 |  | 2026-05-28 | FTR-012 | Shipped
FTR-014 | Platform | Razorpay — payouts | Platform to contributor payout leg | P2 — High | Phase 1 — Hardening | Not Started | In Progress | Not Started |  |  | Backend Lead | Engineering Manager | 2026-07-01 | 2026-07-30 |  | 2026-05-28 | FTR-012 | Conditional on payout go-live
FTR-015 | Platform | Audit log | Immutable audit trail for state changes | P1 — Critical | Phase 1 — MVP | In Progress | Complete | In Progress |  |  | Backend Lead | Engineering Manager | 2026-04-01 | 2026-06-15 |  | 2026-05-28 | FTR-008 | Acceptance decisions persisted
FTR-016 | Platform | Subscription & plan gating | SaaS plan limits, usage, feature gates | P2 — High | Phase 1 — MVP | In Progress | Complete | In Progress |  |  | Full Stack Developer | Engineering Manager | 2026-05-01 | 2026-05-28 |  | 2026-05-28 | FTR-008 | Sidebar plan chip shipped
FTR-017 | Platform | Backend API handoff | External backend team scaffold + contract | P2 — High | Phase 1 — MVP | In Progress | Complete | In Progress |  |  | Engineering Manager | Engineering Manager | 2026-05-01 | 2026-05-28 |  | 2026-05-28 | — | Frontend owns Prisma
FTR-020 | Contributor | Dashboard | Contributor home — tasks, progress, alerts | P1 — Critical | Phase 1 — MVP | In Progress | Complete | In Progress |  |  | Frontend Lead | Engineering Manager | 2026-04-01 | 2026-05-01 |  | 2026-05-28 | FTR-021 | Mock / seed data
FTR-021 | Contributor | Task workroom & lifecycle | Assigned → submit → review → approved flow | P1 — Critical | Phase 1 — MVP | In Progress | Complete | In Progress |  |  | Full Stack Developer | Engineering Manager | 2026-04-15 | 2026-06-30 |  | 2026-05-28 | FTR-090 | localStorage today
FTR-022 | Contributor | Submissions & revisions | Deliverable submit and rework loop | P1 — Critical | Phase 1 — MVP | In Progress | Complete | In Progress |  |  | Full Stack Developer | Engineering Manager | 2026-04-15 | 2026-06-30 |  | 2026-05-28 | FTR-021
FTR-023 | Contributor | Digital twin profile | Skills, evidence, portfolio | P2 — High | Phase 1 — MVP | In Progress | Complete | In Progress |  |  | Full Stack Developer | Engineering Manager | 2026-04-01 | 2026-06-15 |  | 2026-05-28 | —
FTR-024 | Contributor | Onboarding flow | Multi-step contributor registration | P1 — Critical | Phase 1 — MVP | In Progress | Complete | In Progress |  |  | Full Stack Developer | Engineering Manager | 2026-04-01 | 2026-06-01 |  | 2026-05-28 | FTR-002
FTR-025 | Contributor | Earnings & payouts view | Contributor earnings dashboard | P2 — High | Phase 1 — Hardening | In Progress | Complete | Not Started |  |  | Frontend Lead | Engineering Manager | 2026-06-01 | 2026-07-15 |  | 2026-05-28 | FTR-014 | Mock data
FTR-026 | Contributor | Credentials wallet | Issue, share, verify credentials | P2 — High | Phase 1 — MVP | In Progress | Complete | In Progress |  |  | Full Stack Developer | Engineering Manager | 2026-05-01 | 2026-06-30 |  | 2026-05-28 | — | Public share page works
FTR-027 | Contributor | Support & tickets | FAQs, grievances, safety reports | P3 — Medium | Phase 1 — MVP | In Progress | Complete | In Progress |  |  | Full Stack Developer | Engineering Manager | 2026-05-01 | 2026-07-01 |  | 2026-05-28 | —
FTR-028 | Contributor | Community & messages | Community feed and messaging | P3 — Medium | Phase 2 | Deferred | Complete | Not Started |  |  | Frontend Lead | Engineering Manager | 2026-07-01 | 2026-08-01 |  | 2026-05-28 | — | Visual-only mock
FTR-029 | Contributor | Learning recommendations | AI skill learning suggestions | P3 — Medium | Phase 2 | Deferred | Complete | Not Started |  |  | Frontend Lead | Engineering Manager | 2026-07-01 | 2026-08-01 |  | 2026-05-28 | FTR-097
FTR-030 | Contributor | Account auth settings | Password / OAuth / SSO mode selection | P2 — High | Phase 1 — MVP | In Progress | Complete | In Progress |  |  | Full Stack Developer | Engineering Manager | 2026-05-01 | 2026-05-28 |  | 2026-05-28 | FTR-003 | Recently shipped
FTR-040 | Enterprise | Dashboard | Executive dashboard with KPIs and plan usage | P1 — Critical | Phase 1 — MVP | In Progress | Complete | In Progress |  |  | Frontend Lead | Engineering Manager | 2026-04-01 | 2026-05-01 |  | 2026-05-28 | FTR-016
FTR-041 | Enterprise | SOW repository | SOW list and detail views | P1 — Critical | Phase 1 — MVP | In Progress | Complete | In Progress |  |  | Full Stack Developer | Engineering Manager | 2026-04-01 | 2026-06-15 |  | 2026-05-28 | FTR-091 | API + mocks hybrid
FTR-042 | Enterprise | SOW intake (upload + AI) | 5-stage intake wizard with AI extraction | P1 — Critical | Phase 1 — MVP | In Progress | Complete | In Progress |  |  | Full Stack Developer | Engineering Manager | 2026-04-15 | 2026-06-30 |  | 2026-05-28 | FTR-097 | Commit local-state
FTR-043 | Enterprise | SOW approval pipeline | 5-stage commercial / legal sign-off | P1 — Critical | Phase 1 — MVP | In Progress | Complete | In Progress |  |  | Full Stack Developer | Engineering Manager | 2026-04-15 | 2026-06-30 |  | 2026-05-28 | FTR-041
FTR-044 | Enterprise | Decomposition workspace | Break SOW into workstreams and tasks | P1 — Critical | Phase 1 — MVP | In Progress | Complete | Not Started |  |  | Full Stack Developer | Engineering Manager | 2026-05-01 | 2026-07-01 |  | 2026-05-28 | FTR-091 | Mock plans
FTR-045 | Enterprise | Team matching & formation | Suggest and assign contributors | P2 — High | Phase 1 — MVP | In Progress | Complete | Not Started |  |  | Frontend Lead | Engineering Manager | 2026-05-15 | 2026-07-15 |  | 2026-05-28 | FTR-044
FTR-046 | Enterprise | Projects portfolio | Active and completed project tiles | P1 — Critical | Phase 1 — MVP | In Progress | Complete | Not Started |  |  | Full Stack Developer | Engineering Manager | 2026-05-01 | 2026-07-01 |  | 2026-05-28 | FTR-091
FTR-047 | Enterprise | Delivery tracking | Milestones, exceptions, lifecycle view | P1 — Critical | Phase 1 — MVP | In Progress | Complete | Not Started |  |  | Full Stack Developer | Engineering Manager | 2026-05-01 | 2026-07-01 |  | 2026-05-28 | FTR-021
FTR-048 | Enterprise | Review & acceptance queue | Accept / rework deliverables | P1 — Critical | Phase 1 — MVP | In Progress | Complete | In Progress |  |  | Full Stack Developer | Engineering Manager | 2026-04-15 | 2026-06-01 |  | 2026-05-28 | FTR-015 | Postgres audit log
FTR-049 | Enterprise | Reviewer sub-portal | QA inbox, task monitor, metrics | P2 — High | Phase 1 — MVP | In Progress | Complete | Not Started |  |  | Frontend Lead | Engineering Manager | 2026-05-01 | 2026-07-01 |  | 2026-05-28 | —
FTR-050 | Enterprise | Billing overview | Budget, invoices, rate cards UI | P2 — High | Phase 1 — MVP | In Progress | Complete | Not Started |  |  | Full Stack Developer | Engineering Manager | 2026-05-01 | 2026-07-15 |  | 2026-05-28 | FTR-012
FTR-051 | Enterprise | Workforce roster | Internal employee list and profile drawer | P2 — High | Phase 1 — MVP | In Progress | Complete | Not Started |  |  | Full Stack Developer | Engineering Manager | 2026-05-15 | 2026-05-28 |  | 2026-05-28 | FTR-094 | Mock localStorage
FTR-052 | Enterprise | Workforce CSV import | Upload, preview, apply roster | P2 — High | Phase 1 — MVP | In Progress | Complete | Not Started |  |  | Full Stack Developer | Engineering Manager | 2026-05-15 | 2026-06-30 |  | 2026-05-28 | FTR-094
FTR-053 | Enterprise | Manual add employee | Form-based roster provisioning | P2 — High | Phase 1 — MVP | In Progress | Complete | Not Started |  |  | Full Stack Developer | Engineering Manager | 2026-05-15 | 2026-05-28 |  | 2026-05-28 | FTR-051
FTR-054 | Enterprise | Settings — tenant & plan | RBAC settings navigation and workspaces | P2 — High | Phase 1 — MVP | In Progress | Complete | Not Started |  |  | Full Stack Developer | Engineering Manager | 2026-05-01 | 2026-06-15 |  | 2026-05-28 | FTR-093
FTR-055 | Enterprise | Profile & security settings | Sessions, MFA display, security prefs | P2 — High | Phase 1 — MVP | In Progress | Complete | In Progress |  |  | Full Stack Developer | Engineering Manager | 2026-05-01 | 2026-06-15 |  | 2026-05-28 | FTR-004
FTR-056 | Enterprise | Notifications centre | In-app notification feed | P3 — Medium | Phase 1 — MVP | In Progress | Complete | Not Started |  |  | Frontend Lead | Engineering Manager | 2026-05-15 | 2026-07-01 |  | 2026-05-28 | FTR-093
FTR-057 | Enterprise | Enterprise onboarding | First-time admin onboarding flow | P2 — High | Phase 1 — MVP | In Progress | Complete | In Progress |  |  | Full Stack Developer | Engineering Manager | 2026-04-15 | 2026-06-01 |  | 2026-05-28 | —
FTR-058 | Enterprise | Analytics console | Economic and governance analytics | P4 — Low | Phase 2 | Deferred | Complete | Not Started |  |  | Unassigned | Engineering Manager |  | 2026-09-01 |  | 2026-05-28 | — | Phase 2 scope
FTR-059 | Enterprise | Compliance module | ESG, evidence locker, PODL | P4 — Low | Phase 2 | Deferred | Complete | Not Started |  |  | Unassigned | Engineering Manager |  | 2026-09-01 |  | 2026-05-28 | — | Phase 2 scope
FTR-060 | Enterprise | Audit log export | Enterprise audit trail export | P4 — Low | Phase 2 | Deferred | In Progress | In Progress |  |  | Backend Lead | Engineering Manager | 2026-07-01 | 2026-08-01 |  | 2026-05-28 | FTR-015
FTR-070 | Mentor | Dashboard | Mentor home with queue summary | P1 — Critical | Phase 1 — MVP | In Progress | Complete | Not Started |  |  | Frontend Lead | Engineering Manager | 2026-04-01 | 2026-05-01 |  | 2026-05-28 | —
FTR-071 | Mentor | Review queue | Pending submissions awaiting review | P1 — Critical | Phase 1 — MVP | In Progress | Complete | Not Started |  |  | Full Stack Developer | Engineering Manager | 2026-04-15 | 2026-06-30 |  | 2026-05-28 | FTR-092
FTR-072 | Mentor | Active review detail | Rubric scoring and approve / rework | P1 — Critical | Phase 1 — MVP | In Progress | Complete | Not Started |  |  | Full Stack Developer | Engineering Manager | 2026-04-15 | 2026-06-30 |  | 2026-05-28 | FTR-092
FTR-073 | Mentor | Escalation management | Escalated review resolution | P2 — High | Phase 1 — MVP | In Progress | Complete | Not Started |  |  | Frontend Lead | Engineering Manager | 2026-05-01 | 2026-07-01 |  | 2026-05-28 | —
FTR-074 | Mentor | Mentorship sessions | Session notes and history | P2 — High | Phase 1 — MVP | In Progress | Complete | Not Started |  |  | Frontend Lead | Engineering Manager | 2026-05-15 | 2026-07-15 |  | 2026-05-28 | —
FTR-075 | Mentor | Review history | Completed reviews archive | P2 — High | Phase 1 — MVP | In Progress | Complete | Not Started |  |  | Frontend Lead | Engineering Manager | 2026-05-01 | 2026-06-01 |  | 2026-05-28 | —
FTR-076 | Mentor | Profile & settings | Mentor preferences | P3 — Medium | Phase 1 — MVP | In Progress | Complete | Not Started |  |  | Frontend Lead | Engineering Manager | 2026-05-15 | 2026-07-01 |  | 2026-05-28 | —
FTR-080 | Admin | Dashboard | Platform operations overview | P2 — High | Phase 1 — MVP | In Progress | Complete | Not Started |  |  | Frontend Lead | Engineering Manager | 2026-04-01 | 2026-06-01 |  | 2026-05-28 | —
FTR-081 | Admin | Tenant provisioning wizard | Create tenant, tier, invite admin | P2 — High | Phase 1 — MVP | In Progress | Complete | Not Started |  |  | Full Stack Developer | Engineering Manager | 2026-05-01 | 2026-07-01 |  | 2026-05-28 | FTR-008
FTR-082 | Admin | Tenant subscription management | Plan, usage, change history | P2 — High | Phase 1 — MVP | In Progress | Complete | In Progress |  |  | Full Stack Developer | Engineering Manager | 2026-05-01 | 2026-06-15 |  | 2026-05-28 | FTR-016
FTR-083 | Admin | User management | Roles, invitations, directory | P2 — High | Phase 1 — MVP | In Progress | Complete | Not Started |  |  | Full Stack Developer | Engineering Manager | 2026-05-01 | 2026-07-01 |  | 2026-05-28 | FTR-007
FTR-084 | Admin | Email template editor | SOW, OTP, invite templates | P3 — Medium | Phase 1 — MVP | In Progress | Complete | Not Started |  |  | Frontend Lead | Engineering Manager | 2026-05-15 | 2026-07-01 |  | 2026-05-28 | FTR-011
FTR-085 | Admin | Platform pricing config | Contributor rate tables by segment | P3 — Medium | Phase 1 — MVP | In Progress | Complete | In Progress |  |  | Full Stack Developer | Engineering Manager | 2026-05-01 | 2026-06-15 |  | 2026-05-28 | —
FTR-086 | Admin | SOW oversight | Cross-tenant commercial sign-off | P2 — High | Phase 1 — MVP | In Progress | Complete | Not Started |  |  | Frontend Lead | Engineering Manager | 2026-05-01 | 2026-07-01 |  | 2026-05-28 | FTR-041
FTR-087 | Admin | KYC review queue | Contributor onboarding case review | P2 — High | Phase 1 — MVP | In Progress | Complete | Not Started |  |  | Full Stack Developer | Engineering Manager | 2026-05-15 | 2026-07-01 |  | 2026-05-28 | FTR-024
FTR-088 | Admin | Governance & safety reports | Platform-wide triage | P4 — Low | Phase 2 | Deferred | In Progress | Not Started |  |  | Unassigned | Engineering Manager |  | 2026-09-01 |  | 2026-05-28 | —
FTR-090 | Backend | Task persistence (Postgres) | Migrate task store from localStorage | P1 — Critical | Phase 1 — Hardening | Not Started | N/A | Not Started |  |  | Backend Lead | Engineering Manager | 2026-06-01 | 2026-07-15 |  | 2026-05-28 | FTR-008 | Slice 5 — prod blocker
FTR-091 | Backend | SOW / project / decomposition APIs | Prisma models and CRUD endpoints | P1 — Critical | Phase 1 — Hardening | In Progress | N/A | In Progress |  |  | Backend Lead | Engineering Manager | 2026-05-15 | 2026-07-30 |  | 2026-05-28 | FTR-008
FTR-092 | Backend | Mentor decision persistence | Persist approve / rework to database | P1 — Critical | Phase 1 — Hardening | Not Started | N/A | Not Started |  |  | Backend Lead | Engineering Manager | 2026-06-01 | 2026-07-15 |  | 2026-05-28 | FTR-090
FTR-093 | Backend | Settings & preferences API | OperatorPreferences model + endpoints | P2 — High | Phase 1 — Hardening | Not Started | N/A | Not Started |  |  | Backend Lead | Engineering Manager | 2026-06-15 | 2026-07-01 |  | 2026-05-28 | FTR-008
FTR-094 | Backend | Workforce API (production) | Wire workforce routes to Prisma | P2 — High | Phase 1 — Hardening | In Progress | N/A | In Progress |  |  | Backend Lead | Engineering Manager | 2026-05-15 | 2026-07-01 |  | 2026-05-28 | FTR-051
FTR-095 | Backend | Enterprise SSO / HRIS | SAML, OIDC; CSV import path | P2 — High | Phase 1 — Hardening | Not Started | In Progress | Not Started |  |  | Integrations Lead | Engineering Manager | 2026-06-01 | 2026-08-01 |  | 2026-05-28 | FTR-003
FTR-096 | Backend | Outbound webhooks | Jira, Slack, generic connectors | P3 — Medium | Phase 2 | Not Started | N/A | Not Started |  |  | Integrations Lead | Engineering Manager | 2026-07-01 | 2026-08-15 |  | 2026-05-28 | —
FTR-097 | Backend | Assistive AI agents | SOW intake, decomposition, review AI | P2 — High | Phase 1 — Hardening | In Progress | In Progress | In Progress |  |  | AI / ML Engineer | Engineering Manager | 2026-05-01 | 2026-08-01 |  | 2026-05-28 | —
FTR-098 | Backend | Server-side exports | PDF / CSV report generation | P3 — Medium | Phase 2 | Not Started | N/A | Not Started |  |  | Backend Lead | Engineering Manager | 2026-07-01 | 2026-08-01 |  | 2026-05-28 | —
FTR-099 | Backend | Real-time updates (SSE / WS) | Live activity without refresh | P3 — Medium | Phase 2 | Not Started | N/A | Not Started |  |  | DevOps / SRE | Engineering Manager | 2026-08-01 | 2026-09-01 |  | 2026-05-28 | —
FTR-100 | Backend | WCAG 2.1 AA audit | Accessibility compliance gate | P2 — High | Phase 1 — Hardening | Not Started | In Progress | Not Started |  |  | QA Lead | Engineering Manager | 2026-07-01 | 2026-08-30 |  | 2026-05-28 | — | Phase 1D gate

## Dashboard
Program Dashboard
As of 28 May 2026 · sourced from Feature Register
Total features |  | Completed |  | In progress |  | Not started
P1 critical (open) |  | Avg % complete |  | Red / Amber (RAG) |  | Deferred (Phase 2)
By module
Module | Total | Completed | In Progress | Not Started | Avg %
Platform
Contributor
Enterprise
Mentor
Admin
Backend

## Resource Plan
Resource Plan — by assignee
Standard workload view · who owns how many open items
Assigned To | Total assigned | Completed | In progress | Not started | Open P1 items
Product Manager
Engineering Manager
Frontend Lead
Backend Lead
Full Stack Developer
QA Lead
DevOps / SRE
Security Lead
UI/UX Designer
Integrations Lead
AI / ML Engineer

## Definitions
Column & status definitions
Field | Definition
Feature ID | Unique reference (FTR-xxx). Used in dependencies.
Module | Product area: Platform, Contributor, Enterprise, Mentor, Admin, Backend.
Overall Status | Not Started → In Progress → Completed. Also: On Hold, Cancelled, Deferred.
Frontend / Backend Status | Delivery layer status. Use N/A when not applicable (e.g. backend-only).
% Complete | Auto-calculated from overall + FE/BE status.
RAG | Auto: Green (on track), Amber (attention), Red (blocked/overdue risk), Grey (deferred).
Assigned To | Person doing the work (developer / lead).
Accountable (EM) | Manager accountable for delivery sign-off.
Planned Start / End | Baseline schedule dates.
Actual End | Fill when Overall Status = Completed.
Dependency ID | Feature ID that must complete first.
Remarks | Blockers, decisions, links to PRD / ticket.